## Summary
Handover checklist — com.machinarium.notesv2
Generated 2026-10-08 by android-app-builder. Refresh: python3 tools/handover_check.py (keeps the statuses and notes you entered).
Status | Actions
To do | 24
Done | 2
N/A | 0
Release blockers open | 10
Open by owner | Actions
Backend | 3
DevOps | 7
Developer | 4
Product | 10
Release blockers (do these before the first Play upload) |  | Owner
SIGN-1 — Create the release keystore |  | DevOps
SIGN-2 — Add the signing secrets to GitHub |  | DevOps
STORE-1 — Replace the placeholder app icon |  | Product
STORE-2 — Create the Play Console app and store listing |  | Product
STORE-3 — Fill in the Data safety form |  | Product
FB-1 — Create the Firebase project and both Android apps |  | DevOps
FB-2 — Replace the placeholder google-services.json |  | Developer
DL-1 — Publish assetlinks.json on every deep-link host |  | DevOps
DL-0 — Choose the real deep-link hosts |  | Product
API-3 — Replace JSONPlaceholder with the real notes API |  | Backend

## Actions
ID | Area | Task | Why | How | Owner | Release blocker | Verify | Status | Notes
SIGN-1 | Release signing | Create the release keystore | Play only accepts builds signed with your upload key; the project never stores a keystore. | 1. keytool -genkeypair -v -keystore release.jks -alias upload -keyalg RSA -keysize 4096 -validity 10000 2. Store release.jks and both passwords in your password manager (losing them blocks future updates). 3. Enrol in Play App Signing when creating the app (STORE-2). | DevOps | Yes | KEYSTORE_PATH=… ./gradlew :app:bundleProdRelease, then: apksigner verify --print-certs on an APK from the bundle | To do
SIGN-2 | Release signing | Add the signing secrets to GitHub | release.yml builds the signed AAB only when these secrets exist (HARD-07). | GitHub → repo → Settings → Secrets and variables → Actions → New repository secret: KEYSTORE_BASE64 = output of: base64 -i release.jks KEYSTORE_PASSWORD, KEY_ALIAS, KEY_PASSWORD | DevOps | Yes | Push a v* tag → the Release workflow uploads release-aab | To do
CI-1 | CI | Add NVD_API_KEY for the dependency scan | dependency-scan.yml (OWASP) fails or is extremely slow without an NVD API key (HARD-08). | 1. Request a free key at https://nvd.nist.gov/developers/request-an-api-key 2. Add it as the GitHub secret NVD_API_KEY. | DevOps | No | Actions → Dependency scan → Run workflow succeeds | To do
CI-2 | CI | Protect main and require the CI check | The rules are only enforced for humans if a red CI blocks merging (CI-01). | GitHub → Settings → Branches → Add rule for main: require a pull request, require status check 'verify' (CI workflow), block force-pushes. | DevOps | No | Open a PR with a failing test → merge is blocked | To do
STORE-1 | Store | Replace the placeholder app icon | The template ships a placeholder launcher glyph. | Android Studio → New → Image Asset (adaptive + monochrome) → replace app/src/main/res/drawable/ic_launcher_foreground.xml and the ic_launcher_background color. | Product | Yes | Install the app: the launcher shows the real icon (also in themed-icons mode) | To do | auto: placeholder icon still in place
STORE-2 | Store | Create the Play Console app and store listing | Needed before the first upload: listing, content rating, target audience, privacy policy URL. | Play Console → Create app (package com.machinarium.notesv2) → Store listing, App content (content rating, target audience, privacy policy, ads), enable Play App Signing. | Product | Yes | Upload the AAB to the internal testing track without errors | To do
STORE-3 | Store | Fill in the Data safety form | Required by Play; must list what the app and its SDKs collect (Adjust, Appsflyer, Firebase, Firebase Crashlytics, Firebase Cloud Messaging). | Play Console → App content → Data safety. Use each SDK's data-safety guidance; declare encryption in transit (HTTPS only). | Product | Yes | Data safety section shows 'Completed' | To do
STORE-4 | Store | Set the release version | versionCode must grow with every upload; the build reads it from Gradle properties. | CI or local: ./gradlew :app:bundleProdRelease -Papp.versionCode=<n> -Papp.versionName=<x.y.z> | Developer | No | aapt2 dump badging shows the expected versionCode | To do
API-1 | Backend | Confirm the production and stage API URLs | Each flavor reads api.<flavor>.baseUrl; the skill only knew the URL given in intake. | Set api.prod.baseUrl / api.stage.baseUrl in gradle.properties (or ~/.gradle/gradle.properties / CI -P). Include the API version in the path (DATA-07). | Backend | Yes | installStageDebug and installProdDebug both load data | Done | auto: set to https://jsonplaceholder.typicode.com/ — confirm it is production
API-2 | Security | Confirm the certificate pins for the production host | Wrong pins block every request in release builds; the skill read them from the live chain (HARD-01). | 1. Compare api.prod.certPins with the commands in SPEC.md → Hardening (intermediate + root + backup roots). 2. Put a calendar reminder before the intermediate certificate expires. | DevOps | Yes | Release build loads data; a pin mismatch shows an error, not 'no internet' | Done | auto: 4 pins set — confirm against the prod host
ENV-1 | Environments | Provide the stage environment | The stage flavor (com.machinarium.notesv2.stage) talks to api.stage.baseUrl and installs next to prod. | Make sure the stage backend exists and set api.stage.baseUrl / api.stage.certPins. Register com.machinarium.notesv2.stage wherever the prod package is registered (Firebase, deep links, OAuth). | Backend | No | installStageDebug shows 'Stage' in the app name and loads data | To do
FB-1 | Firebase | Create the Firebase project and both Android apps | Analytics, Crashlytics, push, Remote Config and App Distribution need a Firebase project. | Firebase console → Add project → Add Android app twice: com.machinarium.notesv2 and com.machinarium.notesv2.stage (or one project per environment). Add the SHA-1/SHA-256 of the debug and release/upload keys. | DevOps | Yes | Both apps appear in Project settings | To do
FB-2 | Firebase | Replace the placeholder google-services.json | The skill used a placeholder so the build works; real Firebase services need the real file with both clients. | Project settings → Your apps → download google-services.json (it contains both apps) → app/google-services.json. Keep it out of git if the team prefers (CI: store it as a secret and write it in the workflow). | Developer | Yes | App starts and Firebase logs show the project id; handover_check.py marks this Done | To do | auto: placeholder file
FB-3 | Firebase | Enable Crashlytics and test it | Crash reports reach the dashboard only after the first crash from a configured app. | Firebase → Crashlytics → Enable. Trigger a test crash from a debug-only menu, restart the app. | Developer | No | The test crash appears in Crashlytics | To do
PUSH-1 | Push | Set up the backend sender | The app only receives; something must send FCM messages (HTTP v1 API). | Create a service account with the 'Firebase Cloud Messaging API Admin' role; send messages with notification.title/body and data.deeplink (allowed schemes only, PUSH-02). | Backend | No | Firebase console → Messaging → Send test message to a device token | To do
PUSH-2 | Push | Bind PushTokenSink to the backend | Until a PushTokenSink is bound, device tokens are not sent anywhere (PUSH-03). | Implement PushTokenSink in :core:data (register the token through WorkManager with retry) and @Binds it; add the backend endpoint. | Developer | No | Fresh install → backend receives the token | To do | auto: no PushTokenSink implementation yet
RC-1 | Firebase | Create the Remote Config keys | The app gate reads min_version_code (number) and maintenance_mode (boolean); missing keys fall back to the in-app defaults. | Firebase → Remote Config → add min_version_code = 0 and maintenance_mode = false → Publish. Use conditions per app id for stage. | Product | No | Set maintenance_mode=true → the app shows the maintenance screen after the next fetch | To do
DL-1 | Deep links | Publish assetlinks.json on every deep-link host | https App Links open the app only after Android verifies the domain (autoVerify). | Serve https://<host>/.well-known/assetlinks.json listing com.machinarium.notesv2 (and com.machinarium.notesv2.stage on the stage host) with the SHA-256 of the Play App Signing key (Play Console → App integrity). | DevOps | Yes | adb shell pm get-app-links com.machinarium.notesv2 shows 'verified' | To do
AN-firebase | Analytics | Firebase Analytics: check events and conversions | Events are sent once the real google-services.json is in place (FB-2). | Firebase → Analytics → Events: mark key events as conversions; enable DebugView with adb shell setprop debug.firebase.analytics.app com.machinarium.notesv2. | Product | No | DebugView shows the app's events | To do
AN-adjust | Analytics | Adjust: app token and event tokens | Adjust stays off without the app token and only sends events that have a token (OBS-05). | Adjust dashboard → create the app → set analytics.adjust.appToken and analytics.adjust.eventTokens=name:token,… in ~/.gradle/gradle.properties or CI. | Product | No | Sandbox install appears in the Adjust testing console | To do | auto: analytics.adjust.appToken is empty
AN-appsflyer | Analytics | AppsFlyer: dev key | AppsFlyer stays off without the dev key. | AppsFlyer dashboard → App settings → Dev key → analytics.appsflyer.devKey. | Product | No | SDK integration test in the AppsFlyer dashboard passes | To do | auto: analytics.appsflyer.devKey is empty
AN-consent | Analytics | Decide on analytics consent | The composite starts enabled; markets with opt-in rules (e.g. GDPR) need consent first. | If opt-in is required: call analyticsTracker.setEnabled(false) at startup and true after consent; list the SDKs in the privacy policy. | Product | No | With consent off, no provider dashboard receives events | To do
DL-0 | Deep links | Choose the real deep-link hosts | stage.notes.example.com and notes.example.com are placeholders; App Links can't be verified on a domain you don't control. | Pick the domains, then change deepLinkHost(...) for both flavors in app/build.gradle.kts and publish assetlinks.json there (DL-1). | Product | Yes | adb shell am start -a android.intent.action.VIEW -d "https://<host>/notes/1" opens the note | To do
API-3 | Backend | Replace JSONPlaceholder with the real notes API | JSONPlaceholder is a demo API: its write endpoints save nothing, so create/edit/delete stay on the device only and links use local ids. | Agree on the notes API (list, create, update, delete), add the calls in :core:network, and sync LOCAL rows from OfflineFirstNotesRepository (WorkManager). Then carry server ids in deep links (SPEC Known exceptions). | Backend | Yes | A note created on one device appears on another after refresh | To do
FB-4 | Firebase | Turn on R8 mapping upload for Crashlytics | Mapping upload is off by default so builds work without a real Firebase project; without it release stack traces stay obfuscated. | After FB-2, build releases with -Pcrashlytics.uploadMapping=true (add it to release.yml). | DevOps | No | A test crash from a release build shows readable class names in Crashlytics | To do
PUSH-3 | Push | Decide how to handle a permanently denied notification permission | After a permanent denial the rationale card comes back on every start and 'Turn on' can't open the system dialog (audit issue, SPEC Known exceptions). | Persist the answer (DataStore) and hide the card, or link to the app's notification settings instead. | Product | No | Deny twice, restart: no card, or the button opens Settings | To do

## Secrets & keys
Name | What it is | Where it goes | Flavor | How to get it | Read by
KEYSTORE_BASE64 | Base64 of the release/upload keystore | GitHub secret | prod | base64 -i release.jks | .github/workflows/release.yml
KEYSTORE_PASSWORD | Keystore password | GitHub secret | prod | Password manager (SIGN-1) | app/build.gradle.kts (env)
KEY_ALIAS | Key alias (e.g. upload) | GitHub secret | prod | From SIGN-1 | app/build.gradle.kts (env)
KEY_PASSWORD | Key password | GitHub secret | prod | Password manager (SIGN-1) | app/build.gradle.kts (env)
NVD_API_KEY | NVD API key for OWASP dependency-check | GitHub secret | — | nvd.nist.gov developer key | .github/workflows/dependency-scan.yml
api.prod.baseUrl / api.stage.baseUrl | API base URL per environment | gradle.properties or ~/.gradle/gradle.properties or CI -P | prod / stage | Backend team | app/build.gradle.kts → ApiConfig
api.prod.certPins / api.stage.certPins | sha256/… pins (intermediate + root + backups) | gradle.properties | prod / stage | SPEC.md → Hardening commands | app/build.gradle.kts → ApiConfig → NetworkModule
google-services.json | Firebase config for both app ids | app/google-services.json (or CI secret written in the workflow) | both | Firebase → Project settings | google-services Gradle plugin
analytics.adjust.appToken / analytics.adjust.eventTokens | Adjust app token; name:token pairs | ~/.gradle/gradle.properties or CI -P | both | Adjust dashboard | core/analytics BuildConfig
analytics.appsflyer.devKey | AppsFlyer dev key | ~/.gradle/gradle.properties or CI -P | both | AppsFlyer dashboard | core/analytics BuildConfig

## External setup
Service | Setup | Action IDs
GitHub | Secrets (see Secrets & keys) and branch protection on main | SIGN-2, CI-1, CI-2
Google Play Console | App com.machinarium.notesv2, store listing, content rating, target audience, privacy policy, Data safety, Play App Signing, internal testing track | STORE-2, STORE-3
Firebase | Project with apps com.machinarium.notesv2 and com.machinarium.notesv2.stage; SHA fingerprints; download google-services.json | FB-1, FB-2
Firebase Crashlytics | Enable; first test crash | FB-3
Firebase Remote Config | Keys min_version_code (number), maintenance_mode (boolean); publish | RC-1
Firebase Cloud Messaging | Service account for the backend sender (HTTP v1); test message | PUSH-1
Web hosts (your deep-link hosts) | /.well-known/assetlinks.json with the Play App Signing SHA-256 | DL-1
Adjust | App + event tokens | AN-adjust
AppsFlyer | App + dev key | AN-appsflyer

## Verify
Check | Command / steps
Quality gate | python3 tools/check_rules.py . && ./gradlew assembleDebug detekt ktlintCheck lint testDebugUnitTest testStageDebugUnitTest koverVerify
Release build (R8) | ./gradlew :app:bundleProdRelease (signed when KEYSTORE_* are set)
Stage app on a device | ./gradlew :app:installStageDebug
Refresh this checklist | python3 tools/handover_check.py
Deep link opens the right screen | adb shell am start -a android.intent.action.VIEW -d "https://<host>/..." com.machinarium.notesv2
App Links verified | adb shell pm get-app-links com.machinarium.notesv2
Push received | Firebase console → Messaging → Send test message (device token from logcat in debug)
Analytics events | adb shell setprop debug.firebase.analytics.app com.machinarium.notesv2 → Firebase DebugView

## Known exceptions
Source (SPEC.md) | Item
Known exceptions | noteslist and notedetail are one commit: with only the list screen, the app template's `navigateTo` has no caller and the dead-code gate can't pass, so the first feature waited for the second (skill lesson).
Known exceptions | Code review (E4), skipped on purpose: - Notification rationale after a *permanent* denial: the card comes back on the next app start and "Turn on" then does nothing, because telling "never asked" from "permanently denied" needs a stored flag (DataStore), which the app doesn't have. Next step: persist the answer, or open the app's notification settings instead. - Deep links use the local Room id (`/notes/{id}`). Right for links the app builds itself; once a backend sends links, they should carry the server id and resolve it through `remoteId`.
Known exceptions | Build: `gradle/gradle-daemon-jvm.properties` (written by Android Studio) asked for a Java 25 daemon; detekt 1.x can't run on it, so it requires Java 17. Keep it at 17 until detekt 2 is used.